## Overview
TerraFlow Energy — Digital Twin Program
Project Plan & Delivery Roadmap ¦ Executive Summary basis
Program objective
Deliver a physics-accurate, NVIDIA Omniverse/DSX-compatible SimReady OpenUSD digital twin of a flow-battery system, underpinned by a PLM digital-thread that connects requirements, CAD, simulation, test, and change management.
Delivery model
Four dependent phases run sequentially — each phase must be accepted at its gate before the next begins — plus a short mobilization phase and a set of cross-cutting requirements that run for the full program under a single accountable prime contractor.
How to use this plan
The 'Schedule' tab holds the work breakdown and timeline. Durations and start weeks (shown in blue / yellow) are planning ASSUMPTIONS — edit them and the End Week, phase totals, and the visual timeline logic follow. 'Milestones', 'Risks' and 'Cross-Cutting' tabs support governance and gate reviews.
Phase roadmap at a glance
Phase | Focus | Est. duration | Timing (wk) | Exit gate
Mobilization | Governance, charter, architecture vision, RACI | 4 wks | 1–4 | Charter approved
1 · Data & Workflow Backbone | PLM single source of truth, PDM migration, open APIs | 16 wks | 5–20 | G1 Backbone
2 · Tool Connectivity & Pipelines | CAD/P&ID/sim/test integration, CAD→OpenUSD pipeline | 14 wks | 21–34 | G2 Connectivity
3 · Workflow Automation | Event-driven automation, ECRs, KPI dashboards, low-code | 12 wks | 35–46 | G3 Automation
4 · Digital Twin (DSX SimReady) | SimReady OpenUSD twin, FMI/FMU coupling, validation | 20 wks | 47–66 | G4 Twin / go-live
≈66 wks total
Planning assumptions
• Timeline unit is the week; 1 'month' in the Gantt = 4 weeks. Week 1 = program start.
• Durations are indicative order-of-magnitude estimates pending scope, team size, and vendor selection — adjust in the Schedule tab.
• Phases are strictly sequential per the Executive Summary ('each phase must be completed before the next begins').
• Cross-cutting requirements (security, governance, training, SLAs, etc.) run continuously for the whole program.
• A single prime contractor is accountable end-to-end; role names in the Schedule tab are indicative.

## Schedule
Work Breakdown & Schedule
Blue/yellow cells are editable planning inputs · End wk = Start + Dur − 1 · bars are 4-week months
WBS | Task / deliverable | Owner (role) | Depends on | Start wk | Dur (wk) | End wk | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17
MOBILIZATION
0.1 | Program kickoff & governance setup | Prime PM | — | 1 | 2 | 2
0.2 | Prime onboarding, RACI & SLAs baselined | Prime PM | 0.1 | 1 | 3 | 3
0.3 | Program charter & requirements baseline | Systems Eng | 0.1 | 2 | 3 | 4
0.4 | Solution architecture & digital-thread design | Solution Arch | 0.3 | 3 | 2 | 4
G0 | ◆ Gate G0 — Charter & architecture approved | Steering | 0.4 | 4 | 1 | 4 | ◆
PHASE 1 · DATA & WORKFLOW BACKBONE
1.1 | PLM platform selection & environment stand-up | PLM Lead | G0 | 5 | 3 | 7
1.2 | Configure single source of truth / data model | PLM Lead | 1.1 | 8 | 3 | 10
1.3 | Revision & document control | PLM Eng | 1.2 | 10 | 3 | 12
1.4 | BOM management | PLM Eng | 1.2 | 10 | 3 | 12
1.5 | Requirements traceability | Systems Eng | 1.2 | 11 | 3 | 13
1.6 | Change management workflows | PLM Eng | 1.3 | 13 | 3 | 15
1.7 | SolidWorks PDM migration | Data Migration | 1.2 | 12 | 5 | 16
1.8 | Enterprise search | PLM Eng | 1.2 | 14 | 3 | 16
1.9 | Open API layer (REST) | Integration Eng | 1.2 | 15 | 4 | 18
G1 | ◆ Gate G1 — Backbone acceptance | Steering | 1.6,1.7,1.9 | 20 | 1 | 20 |  |  |  |  | ◆
PHASE 2 · TOOL CONNECTIVITY & DATA PIPELINES
2.1 | SolidWorks integration | Integration Eng | G1 | 21 | 3 | 23
2.2 | P&ID tool integration | Integration Eng | G1 | 21 | 3 | 23
2.3 | Simulation tool integration | CAE Eng | G1 | 23 | 4 | 26
2.4 | Test-data ingestion | Data Eng | G1 | 23 | 3 | 25
2.5 | CAD-to-OpenUSD conversion pipeline | USD Pipeline Eng | 2.1 | 25 | 6 | 30
2.6 | Cross-tool data taxonomy | Data Architect | 2.2,2.4 | 27 | 5 | 31
G2 | ◆ Gate G2 — Connectivity acceptance | Steering | 2.5,2.6 | 34 | 1 | 34 | [8 empty] | ◆
PHASE 3 · WORKFLOW AUTOMATION & ORCHESTRATION
3.1 | Event-driven automation engine | Automation Eng | G2 | 35 | 4 | 38
3.2 | Auto task / ECR creation | Automation Eng | 3.1 | 38 | 3 | 40
3.3 | Notifications & escalations | Automation Eng | 3.1 | 39 | 3 | 41
3.4 | KPI dashboards | Analytics Eng | 3.1 | 40 | 4 | 43
3.5 | Low-code workflow authoring | Automation Lead | 3.2 | 42 | 4 | 45
G3 | ◆ Gate G3 — Automation acceptance | Steering | 3.4,3.5 | 46 | 1 | 46 | [11 empty] | ◆
PHASE 4 · DIGITAL TWIN (DSX SIMREADY)
4.1 | SimReady OpenUSD asset build | USD Pipeline Eng | G3 | 47 | 5 | 51
4.2 | Electrochemical model (FMU) | Sim Modeler | G3 | 47 | 6 | 52
4.3 | Thermal model (FMU) | Sim Modeler | G3 | 49 | 5 | 53
4.4 | Hydraulic model (FMU) | Sim Modeler | G3 | 50 | 5 | 54
4.5 | Electrical model (FMU) | Sim Modeler | G3 | 51 | 5 | 55
4.6 | FMI/FMU co-simulation coupling | Sim Integrator | 4.2,4.3,4.4,4.5 | 56 | 4 | 59
4.7 | Omniverse/DSX integration & scene | USD Pipeline Eng | 4.1,4.6 | 58 | 4 | 61
4.8 | Validation against test data | V&V Eng | 4.7 | 61 | 5 | 65
G4 | ◆ Gate G4 — Twin acceptance / go-live ready | Steering | 4.8 | 66 | 1 | 66 | [16 empty] | ◆

## Milestones
Milestones & Phase Gates
Sequential gates — each must be passed before the next phase starts
Gate | Milestone | Target week | Entry criteria (must be complete) | Approver
G0 | Charter & architecture approved | 4 | Governance, RACI, SLAs, charter, requirements baseline, architecture vision | Steering board
G1 | Backbone acceptance | 20 | PLM SSOT live; revision/BOM/traceability/change mgmt; PDM migration; search; open APIs | Steering board
G2 | Connectivity acceptance | 34 | SolidWorks, P&ID, sim & test integrated; CAD→OpenUSD pipeline; data taxonomy | Steering board
G3 | Automation acceptance | 46 | Event-driven automation, ECR creation, notifications/escalations, KPI dashboards, low-code authoring | Steering board
G4 | Digital twin / go-live readiness | 66 | SimReady OpenUSD twin with coupled FMI/FMU models validated against test data | Steering + Sponsor

## Risks
Risk Register
Top program risks — review at every gate
ID | Risk | Ph. | Impact | Likelihood | Mitigation
R1 | Sequential phasing means slippage in one phase pushes all downstream phases | All | High | Medium | Buffer at gates; run cross-cutting & vendor selection early; track critical path weekly
R2 | SolidWorks PDM migration data loss / mapping errors | 1 | High | Medium | Migration dry-runs, checksums, staged cutover, rollback plan
R3 | CAD→OpenUSD conversion fidelity insufficient for SimReady | 2 | High | Medium | Early pipeline spikes; validate geometry/material fidelity against reference assets
R4 | FMI/FMU co-simulation coupling unstable or non-convergent | 4 | High | Medium | Prototype coupling early; define solver tolerances; incremental model integration
R5 | Twin fails validation against physical test data | 4 | High | Medium | Define acceptance tolerances up front; secure test datasets before Phase 4
R6 | Cross-tool taxonomy drift breaks the digital thread | 2 | Medium | Medium | Governed data taxonomy with ownership; automated schema conformance checks
R7 | Single-prime dependency / vendor capability gap | All | Medium | Medium | Capability due diligence; key-personnel clauses; escalation & SLA enforcement
R8 | Security / data-ownership requirements retrofitted late | All | Medium | Low | Treat cross-cutting reqs as continuous; security review at each gate

## Cross-Cutting
Cross-Cutting Requirements & Key Technologies
Continuous across all phases under a single accountable prime contractor
Area | Requirement | Owner (role) | Cadence
Security | Access control, data protection, secure APIs & audit | Security Lead | Continuous / gate review
Governance | Decision rights, RACI, gate approvals, standards conformance | Program Governance | Continuous / gate review
Scalability | Architecture scales with data, users & simulation load | Solution Arch | Design + gate review
Interoperability | Open standards across CAD, PLM, sim, USD | Solution Arch | Continuous
Data ownership | Clear ownership & stewardship across the digital thread | Data Architect | Continuous
Documentation | Living docs for architecture, pipelines & workflows | Tech Writer / Leads | Per deliverable
Training | Role-based enablement for PLM, tools & the twin | Enablement Lead | Per phase rollout
Support SLAs | Defined response/resolution SLAs with the prime | Prime PM | Continuous
Key technologies
PLM backbone · OpenUSD · NVIDIA Omniverse/DSX · SimReady standards · FMI/FMU · REST APIs · CAD integrations · simulation data pipelines · workflow automation · digital-thread architecture